## Project Overview
Scope of Work | Description | Priority | Estimated Timeline | Tools/Technologies | Milestones
Announcements | Manage announcements with like functionality | High | 2 weeks | React, Node.js, MongoDB | Initial API development
News | CRUD operations for news articles | High | 3 weeks | React, Node.js, MongoDB | News feature completed
Calendar | Holiday and company events calendar | Medium | 1.5 weeks | React, Node.js, MongoDB | Calendar UI and API integration
Employee Engagement | Directory, recognition, and communication | High | 4 weeks | React, Node.js, MongoDB | Engagement feature launched
Events | Event management with registration | Medium | 3 weeks | React, Node.js, MongoDB | Event registration live
Social Media | Integration for sharing and displaying posts | Medium | 2 weeks | React, Node.js | Social media functionality complete
Search | Content search functionality | Medium | 2 weeks | Elasticsearch, Node.js | Search feature completed
Knowledge Base | Manage policies, newsletters, and templates | Medium | 4 weeks | React, Node.js, MongoDB | Knowledge base live
User Management | Manage users and roles | High | 3 weeks | Node.js, MongoDB | User management system implemented
Self-Service Workflows | Employee request forms | Medium | 3 weeks | React, Node.js, MongoDB | Workflow system operational
Security | SSO and intranet access controls | High | 2 weeks | OAuth, Node.js | Security features in place
Look and Feel | Design according to branding guidelines | High | 2 weeks | Figma, React | UI/UX design completed
Dashboard | User statistics and engagement metrics | Medium | 3 weeks | React, Node.js, MongoDB | Dashboard launched
Testing | Manual testing and issue resolution | High | 2 weeks | Testing frameworks | Testing complete
Deployment | Cloud/on-premise deployment | High | 1 week | AWS/Azure, Git | Deployment done

## Detailed Breakdown
ID | Feature | Description | Priority
1a | Latest Announcements | Display the latest announcements on the intranet dashboard. | High
1b | Announcements Brief | Provide brief descriptions for each announcement for quick viewing. | Medium
1c | Announcements Details | Show detailed information about each announcement when selected. | Medium
1d | Like | Enable users to like announcements to show appreciation. | Low
2a | Latest News | Display the latest news articles on the intranet. | High
2b | News Brief | Provide brief descriptions for news articles for quick access. | Medium
2c | News Details | Show detailed information about each news article when selected. | Medium
2d | Like | Enable users to like news articles to show appreciation. | Low
3a | Holiday Calendar | Create and maintain a holiday calendar for employees. | High
3b | Company Events Calendar | Create and maintain a calendar for upcoming company events. | High
4a | New Joinee and Birthday Wishes | Automate sending welcome messages for new employees and birthday wishes. | Medium
4b | Employee Directory | Create a searchable directory of employees with contact information. | High
4c | Rewards and Recognition | Implement a system for recognizing and rewarding employee achievements. | Medium
4d | Policies and Employee Communications | Provide easy access to company policies and important communications for employees. | High
4e | Quick Links | Add quick links to frequently used resources on the intranet. | Medium
5a | Upcoming Events | List and manage upcoming events for employees to register. | High
5b | Past Events | Archive past events for future reference. | Medium
5c | Event Registration Form | Create a form for employees to register for events. | High
6a | Social Media Sharing | Enable sharing of announcements/news to social media platforms like LinkedIn. | Medium
7a | Content Search | Implement a search functionality for users to find relevant content easily. | High
7b | Navigation from Search Results | Ensure users can navigate to respective content from search results. | Medium
8a | Policies | Provide a repository of company policies accessible to employees. | High
8b | Newsletters | Archive newsletters for employees to access past editions. | Medium
8c | Templates | Provide templates for various documents needed by employees. | Low
8d | Videos | Host training and informational videos accessible by employees. | Medium
8e | Guidelines | Include guidelines for processes and procedures within the company. | Medium
8f | Job Posting | Allow HR to post job openings on the intranet. | High
8g | Downloadable Content | Enable employees to download relevant documents and forms. | High
9a | User Creation and Management | Create and manage user accounts for employees. | High
9b | Roles and Permissions | Define roles and permissions for users and content access. | High
9c | Role-Based Access Control (RBAC) | Implement RBAC to restrict access based on user roles. | High
9d | User Authentication and Access Control | Ensure secure authentication methods for users accessing the intranet. | High
10a | Employee Self-Service Workflows | Create workflows for employee self-service forms. | Medium
10b | IT Request Forms | Develop various IT request forms for employee use (e.g., CCTV access, user addition). | High
11a | User Login through SSO | Implement Single Sign-On (SSO) for secure and easy user login. | High
11b | Intranet Access Security | Restrict intranet access to company network only. | High
12a | Branding Guidelines | Ensure the intranet design follows company branding guidelines. | High
12b | Header and Footer | Design and implement header and footer for consistency across pages. | Medium
12c | Page Layouts | Create user-friendly page layouts for easy navigation. | Medium
13a | User Access Statistics | Implement tracking for user access statistics. | Medium
13b | Document View and Download Statistics | Track document views and downloads for analysis. | Medium
13c | Employee Engagement Statistics | Monitor employee engagement metrics. | Medium
14a | Manual Testing | Conduct manual testing throughout the development process. | High
14b | Security Issue Resolution | Address any security issues reported by external agencies. | High
15a | Portal Deployment | Deploy the intranet portal on cloud or on-premises as per client requirements. | High
15b | Code Versioning | Implement code versioning and management in the client’s repository. | Medium

## milestone
Phase | Duration | Description | Milestones
Phase 1 | Weeks 1-4 | Requirements gathering and design | - Requirements document finalized
- Initial design mockups created
Phase 2 | Weeks 5-8 | Development of Announcements and News modules | - Announcements module completed
- News module completed
Phase 3 | Weeks 9-12 | Development of Calendar and Employee Engagement modules | - Calendar module completed
- Employee Engagement module completed
Phase 4 | Weeks 13-16 | Development of Events, Social Media, and Search functionalities | - Events module completed
- Social Media integration complete
- Search functionality live
Phase 5 | Weeks 17-20 | Development of Knowledge Base and User Management | - Knowledge Base completed
- User Management system operational
Phase 6 | Weeks 21-24 | Development of Employee Self-Service Workflows and Security features | - Self-Service workflows operational
- Security features implemented
Phase 7 | Weeks 25-28 | Final testing and bug fixing | - Testing completed
- Bug fixing done
Phase 8 | Weeks 29-30 | Deployment and go-live | - Final deployment completed
- Project go-live

## Tools Required
Category | Tool | Description
Development Tools | Visual Studio Code | A powerful code editor with support for extensions and integrations for JavaScript and Node.js development.
| Postman | A tool for testing APIs to ensure they function as expected.
| MongoDB Compass | A GUI for MongoDB to visualize and manage your database.
Version Control | Git | A version control system for tracking changes in your codebase.
| GitHub | A platform for hosting your Git repositories and collaborating with team members.
Front-End Framework | React | A JavaScript library for building user interfaces, specifically single-page applications.
Back-End Framework | Node.js | A runtime environment for executing JavaScript code on the server side.
| Express.js | A web framework for Node.js that simplifies the creation of server-side applications.
Database | MongoDB | A NoSQL database that stores data in flexible, JSON-like documents.
Testing Tools | Jest | A JavaScript testing framework for unit and integration testing.
| Mocha/Chai | Alternative testing frameworks that can be used for backend testing.
Collaboration Tools | Slack | For team communication and collaboration.
| Jira or Trello | Project management tools for task management, sprint planning, and tracking progress.
CI/CD Tools | Jenkins | An automation server for continuous integration and continuous deployment.
| GitHub Actions | A CI/CD tool integrated with GitHub for automating workflows.
Security Tools | OWASP ZAP | An open-source tool for finding vulnerabilities in web applications.
| SonarQube | A tool for continuous inspection of code quality and security.
Deployment Tools | Docker | For containerizing applications to ensure they run in any environment.
| AWS/Azure/Heroku | Cloud platforms for hosting the application.
Monitoring and Analytics | Google Analytics | To track user engagement and traffic.
| Sentry | For real-time error tracking and monitoring of application performance.
Design Tools | Figma or Adobe XD | For UI/UX design and prototyping.